# GREST ODOO ERP IMPLEMENTATION

## Project Framework Document

| Prepared by | samret Singh, Raven Solutions |
| --- | --- |
| Client | Grest |
| Date | February 13, 2025 |
| Status | Discovery Phase - Framework v1.0 |

# TABLE OF CONTENTS

1. Executive Summary

2. Project Scope

3. Discovery Findings

4. Proposed Solution

5. Preliminary Timeline

6. Information Required

7. Risks & Dependencies

8. Success Criteria

9. Next Steps

Appendices

# 1. EXECUTIVE SUMMARY

## Project Objective

Migrate Grest's inventory management and business operations from fragmented Google Sheets-based system to centralized Odoo Community Edition ERP, enabling real-time inventory tracking, automated workflows, and seamless multi-channel sales management.

## Current State

• 15+ Google Sheets managing different aspects of operations

- • 7-8 minute lag for updates to propagate across sheets

- • Manual processes for inventory allocation and tracking

- • Fragmented systems: Separate platforms for B2B, D2C, Retail, Customer Service

- • No single source of truth for inventory status

## Desired State

- • Single centralized ERP system (Odoo Community Edition)

- • Real-time updates across all operations (instant, not 7-8 minutes)

- • Automated workflows for procurement, TRC processing, channel allocation

- • Integrated systems with Shopify (D2C), Grest Partners (B2B), Retail POS

- • Complete visibility of inventory from procurement to sale

## Expected Benefits

- • Time Savings: Eliminate 7-8 minute update lag

- • Accuracy: Reduce manual errors in data entry

- • Visibility: Real-time inventory status across all channels

- • Scalability: Support business growth without system limitations

- • Efficiency: Automated allocation rules and barcode generation

# 2. PROJECT SCOPE

## In Scope

### Core ERP Implementation:

- • Odoo Community Edition installation and configuration ✅ (Completed)

- • Warehouse and location structure setup

- • Inventory management modules

- • Sales and purchase order management

- • Multi-channel inventory allocation

### Data Migration:

- • Import existing inventory from 15 Google Sheets

- • Historical data migration (scope TBD based on data availability)

- • Product catalog setup (iPhone models initially)

- • Contact database migration (suppliers, customers, partners)

### Workflow Automation:

- • Automated barcode generation system

- • Channel allocation rules (B2B, D2C, Retail)

- • TRC (Technical Repair Center) workflow tracking

- • Real-time inventory updates across all touchpoints

### Integrations:

- • Shopify integration for D2C channel (grest.in)

- • Grest Partners platform integration for B2B

- • Customer Service Portal integration (phased approach)

### Custom Development:

- • Custom fields for IMEI tracking, grading, source channels

- • Automated reports replacing current Google Sheets dashboards

- • AI-powered automation for repetitive configuration tasks

## Out of Scope (Future Phases)

- • Rebuilding existing 1,600-parameter grading algorithm

- • Full accounting module implementation (basic tracking only)

- • Mobile app development

- • Complete replacement of retail POS (integration only)

- • HR/Payroll modules

# 3. DISCOVERY FINDINGS

## Process Workflow Overview

Three Parallel Flows Identified:

- 1. Material Flow: Physical movement of devices

- 2. Information Flow: Data tracking via Google Sheets

- 3. Monetary Flow: Financial transactions and approvals

## Key Stakeholders Identified

Operations Team:

- • Warehouse Team (Baljeet): Central inventory management

- • Procurement Team (Ketan): Buyback and supplier management

- • TRC Team (Rajesh, Dinesh): Repairs and quality control

- • Quality Team: Initial and final grading

- • Spareparts Team: Parts inventory management

Sales & Channel Teams:

- • B2B Sales (Aniket): Bulk orders via Grest Partners

- • D2C Manager (Ishani): Online sales via Shopify

- • Retail Manager (Suyash/Sumit): Physical store operations

Support Functions:

- • Accounts Team: Financial tracking and approvals

- • Customer Support: Service portal management

- • IT/Project Manager (Kavita): System coordination

## Pain Points Identified

Critical Issues:

- 1. Update Lag: 7-8 minutes for data to sync across all sheets

- 2. Overselling Risk: Manual blocking system can miss conflicts

- 3. No Real-time Visibility: Can't see inventory status instantly

- 4. Manual Allocation: Channel assignment is time-consuming

- 5. Data Fragmentation: No single source of truth

# 4. PROPOSED SOLUTION

## Architecture Overview

Odoo will serve as the central hub connecting all operations:

INBOUND → ODOO → OUTBOUND

• Procurement    • Warehouse    • B2B Channel

• Buyback       • TRC          • D2C Channel

• Suppliers     • QC           • Retail Stores

## Warehouse Management Structure

Grest Central Warehouse with the following locations:

- • WH/Receiving (Security gate area)

- • WH/Data-Validation (Initial processing)

- • WH/TRC (Technical Repair Center)

- • WH/QC (Quality Check area)

- • WH/Ready-Stock (Graded inventory)

- - B2B-Allocated

- - D2C-Allocated

- - Retail-Allocated

- • WH/Spareparts

## Automation Layer

Immediate Automations:

- • Barcode generation on receipt

- • Real-time inventory updates (eliminate 7-8 min lag)

- • Automatic stock level alerts

Phase 2 Automations:

- • AI-powered channel allocation suggestions

- • Predictive inventory management

- • Automated Excel/Sheet imports

- • Smart reporting and dashboards

# 5. PRELIMINARY TIMELINE

Note: Detailed task-level plan will be provided after Google Sheets analysis

## Week 1: Foundation & Configuration (Feb 13-19)

Objectives: Complete data discovery, configure Odoo core modules, begin initial data migration

Deliverables:

- • Warehouse structure configured

- • Product categories created

- • User accounts and permissions set

- • Sample data imported

Dependencies:

- ⚠️ Access to 15 Google Sheets (PENDING)

- ⚠️ Completed requirements document (PENDING)

- ⚠️ API credentials for integrations (PENDING)

## Week 2: Development & Automation (Feb 20-26)

Build automation scripts, migrate all Google Sheets data, develop custom workflows

## Week 3: Integration & Testing (Feb 27 - Mar 5)

Integrate external systems, user acceptance testing, training materials creation

## Week 4: Go-Live Preparation (Mar 6-12)

Parallel run with Google Sheets, issue resolution, final data sync

# 6. INFORMATION REQUIRED FOR DETAILED PLANNING

## CRITICAL (Required This Week)

From Kavita:

- 1. Google Sheets Access

- View or export access to all 15 operational sheets

- Column structure and data dictionary

- Sample data (or anonymized data)

- Understanding of sheet relationships

- 2. Completed Requirements Document

- 58-question questionnaire (sent separately)

- Business rules documentation

- User role definitions

- Report requirements

- 3. Technical Details

- Current barcode format and generation logic

- Grading algorithm details (integration approach)

- API documentation for existing systems

- User access requirements

- 4. Data Specifications

- Current inventory count

- Number of SKUs (product variations)

- Transaction volume (daily/weekly)

- Historical data retention needs

# 7. RISKS & DEPENDENCIES

## High Risk

### 1. Data Quality & Complexity

- • Risk: Google Sheets data may be inconsistent or incomplete

- • Impact: Delayed migration, data cleanup required

- • Mitigation: Early access to sheets for assessment, data validation scripts

### 2. Integration Complexity

- • Risk: External system APIs may not support required functionality

- • Impact: Manual processes remain, reduced automation

- • Mitigation: Early API testing, fallback to manual processes if needed

### 3. User Adoption

- • Risk: Team resistance to new system

- • Impact: Continued use of old sheets, system not utilized

- • Mitigation: Thorough training, parallel run period, champion users

## Medium Risk

### 4. Timeline Dependency on Information

- • Risk: Delayed access to Google Sheets or documentation

- • Impact: Project timeline pushed back

- • Mitigation: Clear communication, escalation path through Kavita

# 8. SUCCESS CRITERIA

## Technical Success

- ✅ All 15 Google Sheets data migrated successfully

- ✅ Real-time updates working (no 7-8 minute lag)

- ✅ Shopify integration functional

- ✅ Barcode system operational

- ✅ All user accounts and permissions configured

- ✅ Reports matching current Google Sheets functionality

## Business Success

- ✅ Warehouse team can track inventory in real-time

- ✅ Sales team can allocate inventory without conflicts

- ✅ Accounts team has accurate financial data

- ✅ No revenue loss during transition

- ✅ Improved operational efficiency (measurable time savings)

## User Adoption Success

- ✅ All key users trained and comfortable

- ✅ Google Sheets discontinued after go-live

- ✅ Positive feedback from operational teams

- ✅ Support tickets manageable and decreasing

# 9. NEXT STEPS

## Immediate Actions (This Week)

Raven Solutions (samret):

- 1. ✅ Share this framework with Grest management

- 2. ⏳ Request access to 15 Google Sheets from Kavita

- 3. ⏳ Follow up on requirements questionnaire completion

- 4. ⏳ Schedule technical clarification call with Kavita

- 5. ⏳ Begin Odoo module exploration and configuration testing

Grest (Kavita/Aditya):

- 1. ⏳ Provide access to Google Sheets (view or export)

- 2. ⏳ Complete requirements questionnaire document

- 3. ⏳ Share API documentation for existing systems

- 4. ⏳ Identify and confirm key user contacts

- 5. ⏳ Confirm project timeline and go-live target date

## This Week Milestones

By Friday, Feb 14:

- • Google Sheets access received

- • Requirements document completed

- • Technical clarification call completed

By Monday, Feb 17:

- • Detailed project plan published

- • Week 1 development work begins

- • Data migration strategy finalized

# APPENDICES

## A. Technology Stack

- • Odoo Community Edition 18

- • PostgreSQL database

- • Ubuntu 24 server (VPS-2)

- • Reverse proxy: Caddy (subdomain: godoo.sam9scloud.in)

## B. Glossary

- • TRC: Technical Repair Center

- • QC: Quality Check

- • C2B: Customer to Business (buyback)

- • B2B: Business to Business (bulk sales)

- • D2C/B2C: Direct to Consumer (online sales)

- • IMEI: International Mobile Equipment Identity

- • SKU: Stock Keeping Unit (product variant)

- • ERP: Enterprise Resource Planning

# DOCUMENT CONTROL

Next Review: After Google Sheets analysis (Expected: Feb 14, 2025)

________________________________________________________________________________

END OF FRAMEWORK DOCUMENT

Detailed project plan with day-by-day tasks will be provided
once critical information is received.