Table of Contents

# GREST ODOO ERP - COMPREHENSIVE PROJECT PLAN

## Version 2.0 - Updated After Meeting Analysis

Prepared by: Samret Singh
Date: February 24, 2025
Status: READY FOR STAKEHOLDER REVIEW

Major Changes in v2.0: - ✅ Added Procurement module (new discovery) - ✅ Updated TRC architecture (P&L-driven routing, not grade-driven) - ✅ Added Cannibalization workflow - ✅ Added Exception states (SCRAP, LOST, RETURNED) - ✅ Revised timeline: 14 weeks (was 12) - ✅ New state machine with profit-driven decision logic

## PROJECT OVERVIEW

### What We’re Building

A complete ERP system on Odoo Community Edition replacing 30+ Google Sheets for Grest’s refurbished device business — tracking every device from procurement through quality check, repair, and multi-channel sales.

CRITICAL INSIGHT: This is not just inventory management. This is reverse-engineering a living business organism with judgment-heavy decision-making into a structured ERP system.

### Technology Stack

- Platform: Odoo 18 Community (installed ✅ at godoo.sam9scloud.in)

- Database: PostgreSQL (grest_production ✅)

- Custom Modules: Python + XML

- Deployment: VPS-2 (connected ✅)

- Migration: Python scripts via Odoo XML-RPC API

### Key Numbers

| Metric | Value |
| --- | --- |
| Total Users | ~100 |
| Devices in inventory | ~100,000 |
| Weekly intake | ~1,000 devices |
| Spare parts records | ~10,000+ |
| Repair records | 6,547 |
| Product models | 106+ |
| Brands | 24 |
| Vendors/Suppliers | 30 |
| Warehouse locations | GRG (Gurgaon) + others |
| Cannibalization rate | ~1 in 100 devices |

## THE THREE CORE BUSINESS ENGINES

Based analysis, Grest’s business consists of three interconnected engines:

### Engine 1: Intake Engine

Procurement → Warehouse Identity Creation

Components:
- GRN generation (Procurement reference number)
- GSN generation (Warehouse barcode = PRIMARY unique ID)
- Physical handover & acceptance workflow
- Device rejection capability

### Engine 2: Evaluation Engine ⚠️ MOST COMPLEX

TRC + P&L Decision Logic

Process:
1. ELS → Grade assignment (DESCRIPTIVE only, not routing)
2. P&L Calculation:
   - Purchase price (from procurement)
   - Current sale value (as-is condition)
   - Post-repair sale value (estimated)
   - Repair cost (manually entered by TRC)
   - Margin comparison
3. Routing Decision (PROFIT-DRIVEN):
   - IF Post-Repair Margin > Current Margin + Threshold → REPAIR
   - IF Current Margin better → SELL AS-IS
   - IF Both negative → CANNIBALIZE/SCRAP/RETURN

KEY INSIGHT: Grade does NOT determine routing. P&L does.

### Engine 3: Disposition Engine

Final State Transition & Financial Closure

Options:
- Sell via channels (B2B/B2C(D2C)/B2R)
- Cannibalize (harvest valuable parts, close GSN auditably)
- Scrap (total loss, financial write-off)
- Return to Supplier (procurement reversal, rare exception)
- Mark as LOST (Admin only, theft/shrinkage) Add others.

Everything else = Inventory accounting around these three engines

## UPDATED MODULE ARCHITECTURE

### Module 1: grest_procurement (NEW)

Purpose: Initial device intake and GRN management

Features: - GRN (Goods Receipt Note) generation - Supplier tracking - Batch management - IMEI/Model/Price capture - Procurement → Warehouse handover workflow

Data captured: - Supplier name & code - Batch ID - Device IMEI - Model details - Purchase price per device - Expected condition/grade - Accessories included (if any)

Handover to Warehouse: - Physical handover document - Warehouse acceptance/rejection capability - GRN linked to GSN for traceability

### Module 2: grest_warehouse

Purpose: Device identity creation and location management

Features: - GSN (Barcode) generation = PRIMARY unique identifier - Barcode printing - Location tracking (GRG/Input, GRG/Purchase-IN, GRG/TRC, etc.) - Acceptance/Rejection workflow - Transfer to TRC decision - Channel allocation (after TRC clearance)

Barcode Format:

[BrandCode][LocationCode][Category][Sequence]
Example: APGRGA001

Brand Codes:
AP = Apple, SA = Samsung, ON = OnePlus, XI = Xiaomi,
VI = Vivo, OP = Oppo, MO = Motorola, GO = Google, RE = Realme

Locations:

GRG/Input               (Security gate receiving)
GRG/Purchase-IN         (Warehouse acceptance area)
GRG/TRC                 (Technical Repair Center)
GRG/QC                  (Quality Control - if separate from TRC)
GRG/Ready-Stock         (Post-QC, ready for sale)
GRG/B2B                 (B2B allocated)
GRG/D2C                 (Direct to Consumer allocated)
GRG/B2R                 (Business to Retail allocated)
GRG/MG-Store            (MG Road retail)
GRG/Spareparts          (Spare parts storage)

### Module 3: grest_trc (Evaluation Engine - MOST COMPLEX)

Purpose: Device evaluation, P&L-driven routing, repair execution

Stage-Based Workflow:

#### Stage 1: ELS (Entry Level Screening)

- Grade assignment (DESCRIPTIVE, not routing decision)

- Issues identification

- Visual inspection

- Functional testing (basic)

- Output: ELS Grade + Issues List

#### Stage 2: P&L Calculation ⚠️ CORE DECISION ENGINE

Calculation Form (ASSISTED - System calculates, human decides):

Inputs:
1. Purchase Price: ₹6,850 (auto-filled from procurement)
2. Current Sale Price (as-is): ₹8,500 (auto from pricelist)
3. Post-Repair Sale Price: ₹11,000 (auto from pricelist)
4. Estimated Repair Cost:
   - Parts cost: ₹1,200 (MANUAL entry by TRC - market call)
   - Labor cost: ₹400 (MANUAL entry or standard rate)
   - Total Repair Cost: ₹1,600

Calculation:
Current Margin = 8,500 - 6,850 = ₹1,650
Post-Repair Margin = 11,000 - 6,850 - 1,600 = ₹2,550
Margin Improvement = 2,550 - 1,650 = ₹900

Decision Logic:
IF Margin Improvement > Threshold (e.g., ₹500) → REPAIR RECOMMENDED
IF Current Margin better → SELL AS-IS RECOMMENDED
IF Both negative → CANNIBALIZE/SCRAP/RETURN

Final Decision: TRC Manager (can override with reason)

Thresholds (TO BE CLARIFIED WEDNESDAY): - Minimum acceptable margin %? - Maximum repair cost ratio? - Loss escalation rules? - Loss < ₹500 → TRC Manager approves - Loss ₹500-2000 → Finance approval - Loss > ₹2000 → Admin approval

#### Stage 3: Repair Execution (if approved)

- Assignment to repair technician

- Spare parts consumption tracking (auto-deduct from inventory)

- Labor hours logging

- Cost accumulation

- Post-repair testing

#### Stage 4: FQC (Final Quality Check)

- Final grade assignment

- Post-repair inspection

- Can FAIL → back to repair or escalate to scrap

- FQC Grade = Final Sales Grade

#### Stage 5: Disposition Decision

Routing Options: 1. Return to Warehouse (for sale) → WAREHOUSE_READY_FOR_SALE 2. Cannibalize → CANNIBALIZED state + parts to spare inventory 3. Scrap → SCRAPPED state + financial write-off 4. Return to Supplier → RETURNED_TO_SUPPLIER (exception)

### Module 4: grest_cannibalization (NEW - CRITICAL)

Purpose: Handle non-viable devices through part harvesting

Cannibalization Workflow:

Trigger: P&L shows device unprofitable for repair or sale
Decision: TRC Manager approves cannibalization
Execution:
  1. Technician harvests valuable parts
  2. Parts enter spare inventory with valuation
  3. Device GSN transitions to CANNIBALIZED state
  4. Financial closure: Device book value allocated to harvested parts
  5. GSN closed but remains auditable (not deleted)

Accounting Questions (TO BE CLARIFIED WEDNESDAY): - At what valuation do harvested parts enter inventory? - Device book value / # of parts? - Market value of parts? - Fixed recovery rate? - Is harvesting labor tracked and allocated? - How is device book value transferred to parts?

Example:

Device: iPhone 11 (APGRGA123)
Purchase Price: ₹6,500
Repair Cost if attempted: ₹3,000
Sale Value (repaired): ₹8,000
Result: LOSS of ₹1,500 if repaired

Cannibalization Decision:
Harvest:
  - Display (Original): Market value ₹1,800
  - Battery (OEM): Market value ₹500
  - Back Housing(The metal or plastic skeleton that holds the internal components ): Market value ₹400
Total Harvested Value: ₹2,700
Net Recovery: ₹2,700 vs. Loss of ₹1,500
Decision: CANNIBALIZE

Result:
  - 3 parts added to spare inventory
  - Device GSN = CANNIBALIZED (auditable)
  - Financial: Recovered ₹2,700 value

### Module 5: grest_spares

Purpose: Spare parts inventory and cost management

Features: - Spare parts catalog - Part-to-model compatibility mapping - Quality grades (Original/OEM/Compatible) - Market price tracking - Consumption tracking during repair - Harvested parts from cannibalization

Part Categories: - Display - Battery - Front Glass - Back Panel/Housing - Child Parts (camera, flex, ringer, etc.) - Consumables & Tools

Auto-deduction during repair: When technician logs parts used → Inventory auto-decrements → Cost auto-adds to device repair cost

### Module 6: grest_sales

Purpose: Channel allocation and sales execution

Features: - Channel allocation (B2B/B2C/B2R) - Sales order creation - Inventory out tracking - Pricing by grade and channel

Channel Names (FINAL - To be confirmed Wednesday): - B2B: Business to Business (bulk buyers) – B2C / D2C: Business to Consumer (website, direct customers) - B2R: Business to Retail (retailers who resell) - E-COM: Amazon/Flipkart (separate or part of B2C?) - Retail: MG Road store (separate or part of B2C?)

### Module 7: grest_dashboard

Purpose: Real-time business intelligence

Dashboard Sections:

1. Inventory Status: - Total devices in system - By location (Purchase-IN, TRC, Ready-Stock, etc.) - By channel allocation - Aging analysis (0-30, 30-60, 60-90, 90-180, 180+ days)

2. TRC Operations: - Devices in ELS - Devices awaiting P&L decision - Devices in repair - Average repair TAT (Turnaround Time)

3. Exception Tracking (NEW): - Devices cannibalized (count & value recovered) - Devices scrapped (count & loss) - Devices lost (count & loss) - Devices returned to supplier (count) - Devices in loss-making repair (count & total loss)

4. Financial Metrics: - Total inventory value - Margin by channel - Repair cost vs. value improvement - Loss/recovery from cannibalization

## COMPLETE STATE MACHINE (UPDATED)

PROCUREMENT_IN
  ↓ (Procurement creates GRN, enters IMEI/model/price)
PROCUREMENT_READY_FOR_WAREHOUSE
  ↓ (Physical handover to warehouse)
WAREHOUSE_PENDING_ACCEPTANCE
  ↓ (Warehouse inspects, can ACCEPT or REJECT)
  ├─→ REJECTED → Return to Procurement/Supplier
  └─→ ACCEPTED
       ↓ (GSN generated = PRIMARY unique identifier)
       WAREHOUSE_READY
       ↓ (Transfer decision)
       ├─→ WAREHOUSE_READY_FOR_SALE (if no TRC needed - rare)
       └─→ TRC_IN
            ↓
            TRC_ELS (Engineering Level Sorting) 
            ↓ (Grade assigned - DESCRIPTIVE only)
            TRC_P&L_EVALUATION
            ↓ (Margin calculation - ASSISTED decision)
            │
            ├─→ TRC_REPAIR_APPROVED (margin improvement justifies repair)
            │    ↓ (Parts assigned, technician assigned)
            │    TRC_REPAIR_IN_PROGRESS
            │    ↓ (Spare parts auto-deducted, labor logged)
            │    TRC_REPAIR_COMPLETE
            │    ↓
            │    TRC_FQC (Final Quality Control)
            │    ↓ (Final grade assignment)
            │    ├─→ FQC_PASS → WAREHOUSE_READY_FOR_SALE
            │    └─→ FQC_FAIL → Back to TRC_REPAIR or SCRAP
            │
            ├─→ TRC_SELL_AS_IS (current margin better than post-repair)
            │    └─→ WAREHOUSE_READY_FOR_SALE
            │
            ├─→ CANNIBALIZED (harvest valuable parts)
            │    ├─→ Parts added to spare inventory (valuation TBD)
            │    ├─→ Device book value allocated to parts
            │    └─→ GSN closed (auditable, not deleted)
            │
            ├─→ SCRAPPED (total loss, no recovery value)
            │    ├─→ Financial write-off
            │    └─→ GSN closed (auditable)
            │
            └─→ RETURNED_TO_SUPPLIER (exception - dispute/defect)
                 ├─→ Procurement reversal
                 └─→ GSN closed (auditable)

WAREHOUSE_READY_FOR_SALE
  ↓ (Channel allocation decision)
  ├─→ B2B_ALLOCATED
  ├─→ B2C_ALLOCATED
  └─→ B2R_ALLOCATED
       ↓ (Sale execution)
       SOLD
       ↓
       CLOSED (GSN archived)

Exception States (Admin only - high security):
- LOST (theft/misplaced)
- DEMO_LOST (showroom loss)

State Transition Authority (TO BE CLARIFIED WEDNESDAY):

| Transition | Authority | Can Override? | Override By |
| --- | --- | --- | --- |
| Procurement → Warehouse | Procurement Mgr | - | - |
| Warehouse Accept/Reject | Warehouse TL | - | - |
| Warehouse → TRC | Warehouse TL | - | - |
| TRC → Repair (approved) | TRC Manager | Yes (if loss) | Finance |
| TRC → Sell As-Is | TRC Manager | - | - |
| TRC → Cannibalize | TRC Manager | Yes | Admin |
| TRC → Scrap | TRC Manager | Yes | Finance |
| TRC → Return to Supplier | TRC Manager | Yes | Finance + Admin |
| Warehouse → Sales Channel | Sales Team Lead | - | - |
| Any → LOST/DEMO_LOST | - | - | Admin ONLY |

### PHASE 1: INTAKE ENGINE (3 weeks)

Weeks 3-5 | Procurement + Warehouse Modules

Goal: Set up device intake from procurement through warehouse

#### Week 3: Odoo Configuration

Day 1-2: Procurement Module Setup - Create Procurement module structure - GRN sequence configuration - Supplier management - Batch tracking - Procurement forms (IMEI, Model, Price entry)

Day 3-4: Warehouse Module Setup - GSN/Barcode generation logic - Barcode printer integration - Location hierarchy (GRG/Input, GRG/Purchase-IN, etc.) - Acceptance/Rejection workflow

Day 5: Handover Workflow - Procurement → Warehouse transfer - Acceptance inspection form - Rejection reason codes - GRN ← → GSN linkage

#### Week 4: Data Foundation

Day 1-2: Master Data Import - Vendors (30 suppliers) - Product catalog (106+ models) - Pricelists (grade-based pricing)

Day 3-4: User Accounts - Procurement team users - Warehouse team users - Role-based permissions - Location-based access

Day 5: Testing - End-to-end test: Procurement → Warehouse - Barcode printing test - Acceptance/rejection test

#### Week 5: Historical Data Migration

Script: 01_import_historical_procurement.py - Import procurement records (if any) - Link to warehouse receipts - Verify GRN → GSN mapping

Deliverables: - ✅ Procurement module operational - ✅ Warehouse module operational - ✅ Barcode generation working - ✅ GRN → GSN linkage verified - ✅ Historical data imported

### PHASE 2: EVALUATION ENGINE (4 weeks) ⚠️ MOST COMPLEX

Weeks 6-9 | TRC Module + P&L Logic

Goal: Build profit-driven evaluation and routing system

#### Week 6: TRC Module Foundation

Day 1-2: Module Structure - Create grest_trc module - Define stages (ELS, P&L, Repair, FQC, Disposition) - Device record model with stages

Day 3-4: ELS Workflow - ELS inspection form - Grade assignment (descriptive) - Issues tracking - Visual/functional checklist

Day 5: ELS → P&L Transition - Stage transition logic - Grade stored but NOT used for routing - Device ready for P&L evaluation

#### Week 7: P&L Calculation Engine ⚠️ CRITICAL

Day 1-3: P&L Calculator Form

Form Fields:
1. Purchase Price (auto-filled, read-only)
2. Current Sale Price (auto from pricelist based on ELS grade)
3. Post-Repair Sale Price (auto from pricelist, grade improved)
4. Estimated Repair Cost:
   - Parts cost (MANUAL entry with validation)
   - Labor cost (MANUAL entry or standard rate)
5. Calculations (auto):
   - Current Margin = Sale (as-is) - Purchase
   - Post-Repair Margin = Sale (repaired) - Purchase - Repair Cost
   - Margin Improvement = Post-Repair - Current
6. Recommendation (auto):
   - IF Improvement > Threshold → REPAIR
   - IF Current better → SELL AS-IS
   - IF Both negative → CANNIBALIZE/SCRAP
7. TRC Manager Decision (MANUAL override possible)
8. Override Reason (if decision differs from recommendation)

Day 4-5: Routing Logic Implementation - Decision logic based on P&L - Threshold configuration - Override/escalation workflow - Loss approval (Finance/Admin)

#### Week 8: Repair Workflow

Day 1-2: Repair Execution - Technician assignment - Spare parts selection (auto-suggest based on model) - Parts consumption (auto-deduct from inventory) - Labor logging

Day 3-4: FQC Workflow - Post-repair inspection form - Final grade assignment - FQC pass/fail logic - Fail → back to repair or scrap escalation

Day 5: Testing - End-to-end TRC flow - P&L calculation accuracy - Routing decision verification

#### Week 9: Cannibalization & Exception Flows

Day 1-2: Cannibalization Workflow - Cannibalization approval form - Part harvesting tracking - Parts-to-inventory transfer - Valuation logic (based on Wednesday answers) - GSN closure (auditable)

Day 3: Exception States - SCRAP workflow + financial write-off - LOST state (Admin only) - RETURNED_TO_SUPPLIER workflow

Day 4-5: Historical TRC Data Migration - Script: 02_import_trc_records.py - Import ELS/FQC records (2,336 records) - Import repair records (6,547 records) - Link to current devices

Deliverables: - ✅ TRC module operational with all stages - ✅ P&L calculator working - ✅ Profit-driven routing logic verified - ✅ Cannibalization workflow tested - ✅ Exception states implemented - ✅ Historical TRC data imported

### PHASE 3: DISPOSITION ENGINE (3 weeks)

Weeks 10-12 | Sales + Spares + Dashboard

#### Week 10: Spare Parts Module

Day 1-2: Spares Catalog - Spare parts product catalog - Part-to-model compatibility mapping - Quality grades (OG/OEM/Compatible)

Day 3-4: Inventory Management - Spare parts locations - Stock tracking - Market price tracking - Consumption during repair (auto-deduct) - Harvested parts from cannibalization

Day 5: Historical Spares Data - Script: 03_import_spare_parts.py - Import 8,000+ spare parts records

#### Week 11: Sales Module

Day 1-2: Channel Allocation - B2B/B2C/B2R allocation logic - Allocation forms - Channel-specific pricing

Day 3-4: Sales Orders - Sales order creation - Inventory out tracking - Invoice generation

Day 5: Historical Sales Data - Script: 04_import_sales_data.py - Import historical sales records

#### Week 12: Dashboard

Day 1-3: Dashboard Development - Real-time inventory metrics - TRC operations monitoring - Exception tracking (NEW): - Cannibalized devices (count & value) - Scrapped devices (count & loss) - Lost devices (count & loss) - Financial summaries

Day 4-5: Testing & Refinement - End-to-end system test - Performance optimization - User acceptance testing prep

Deliverables: - ✅ Spare parts module operational - ✅ Sales module operational - ✅ Dashboard with exception tracking - ✅ All historical data imported

### PHASE 4: INTEGRATION & TRAINING (2 weeks)

Weeks 13-14 | External Systems + User Adoption

#### Week 13: Integration

Day 1-3: Shopify Integration (if critical - TBD Wednesday) - Inventory sync (Odoo → Shopify) - Order sync (Shopify → Odoo) - Real-time updates - Testing with live data

Day 4-5: Grest Partners Integration (if applicable) - API integration (if available) - Manual export workflow (if no API)

#### Week 14: Training & Go-Live Prep

Day 1: Procurement Team Training - GRN creation - Device data entry - Handover to warehouse

Day 2: Warehouse Team Training - Acceptance/rejection - Barcode generation - Location management - Transfer to TRC

Day 3: TRC Team Training - ELS process - P&L calculator usage - Repair execution - Cannibalization workflow

Day 4: Sales Team Training - Channel allocation - Sales order creation - Inventory viewing

Day 5: Management Training - Dashboard overview - Reports and exports - User management - Exception monitoring

Deliverables: - ✅ Shopify integration (if critical) - ✅ All teams trained - ✅ User manuals created - ✅ System ready for parallel run

### PHASE 5: GO-LIVE (Parallel Run + Cutover)

Weeks 15-16 | Parallel Operation + Final Transition

#### Week 15: Parallel Run

- ALL operations in BOTH Google Sheets AND Odoo

- Daily reconciliation

- Issue tracking and resolution

#### Week 16: Cutover

- Day 1-3: Final data sync

- Day 4: Google Sheets go READ-ONLY

- Day 5: Odoo becomes system of record

- Week 17+: Hypercare

Deliverables: - ✅ Odoo is primary system - ✅ Google Sheets retired - ✅ Zero inventory discrepancy - ✅ All stakeholders comfortable

## CRITICAL DEPENDENCIES & RISKS

### Dependencies:

From Wednesday Meeting: 1. P&L threshold values (min margin %, escalation rules) 2. Cannibalization accounting rules (valuation method) 3. Authority matrix (who approves what) 4. Automation levels (automated/assisted/manual decisions) 5. Shopify integration priority (critical or can wait)

Technical: 1. Odoo MCP connection stable (✅ Working) 2. c deployment pipeline (✅ Connected) 3. VPS server capacity (needs monitoring with 100K devices)

### Risks & Mitigation:

Risk 1: P&L Logic Too Complex - Mitigation: Build P&L calculator as ASSISTED tool (system recommends, human decides) - Fallback: Keep manual override capability with required justification

Risk 2: Cannibalization Accounting Unclear - Mitigation: MUST clarify in Wednesday meeting - Blocker: Cannot build module without valuation rules - Escalation: If not clear, phase cannibalization to Phase 6 (post go-live)

Risk 3: User Adoption Resistance - Mitigation: Champion users in each department - Strategy: Show P&L calculator value early (Week 7) - Training: Hands-on, not just presentation

Risk 4: Data Quality in Migration - Mitigation: Validate before import, fix errors iteratively - Strategy: Import in stages, verify each stage before next

Risk 5: Scope Creep - Mitigation: Phase 0 sign-off acts as baseline - Rule: New requirements go to Phase 6 (future enhancements)

## SUCCESS CRITERIA

### Technical Success:

- ☐ All 100+ users can login with correct permissions

- ☐ Any device findable by IMEI/GSN in < 3 seconds

- ☐ P&L calculator shows correct margin calculations

- ☐ Cannibalization workflow tracks parts correctly

- ☐ Barcode generation and printing works

- ☐ Real-time dashboard updates within 1 second

- ☐ Zero data loss in migration

- ☐ System handles 1,000 devices/week intake

### Business Success:

- ☐ TRC Manager can make repair decisions based on P&L in Odoo

- ☐ Warehouse can track device location in real-time

- ☐ Sales team can see allocated inventory instantly

- ☐ Management can view exception tracking (cannibalized, lost, scrapped)

- ☐ Google Sheets officially retired

- ☐ Zero inventory discrepancy (Odoo vs. physical count)

- ☐ Profit margins improved due to better decision visibility

## WHAT’S DIFFERENT IN V2.0?

Major Additions: 1. ✅ Procurement Module - New discovery from meeting 2. ✅ P&L-Driven Routing - Grade is descriptive, not routing decision 3. ✅ Cannibalization Workflow - Real business flow, not edge case 4. ✅ Exception States - SCRAP, LOST, RETURNED as explicit states 5. ✅ Authority Matrix - Who approves what (to be filled Wednesday) 6. ✅ Phase 0 - Requirements finalization (2 weeks added)

Architectural Changes: 1. ✅ TRC is now “Evaluation Engine” with P&L at core 2. ✅ Complete state machine with profit-driven logic 3. ✅ Dashboard includes exception tracking 4. ✅ Spare parts module includes harvested parts

Timeline Changes: - v1.0: 12 weeks - v2.0: 14 weeks (+2 weeks for requirements finalization)

Philosophy Change: - v1.0: Assumed clear business rules - v2.0: Acknowledges judgment-heavy decision making and builds ASSISTED systems to support (not replace) human judgment

## NEXT STEPS

### Before Wednesday Meeting:

- ✅ Questionnaire v3 prepared

- ⏳ Print questionnaire

- ⏳ Schedule 3-hour meeting (minimum!)

- ⏳ Ensure ALL stakeholders attend:

  - Procurement team member

  - Balpreet (Warehouse TL)

  - Ketan (TRC Manager)

  - Sales team lead

  - Kavita (coordination)

  - Sanjeev (if available)

### During Wednesday Meeting:

- Complete Questionnaire v3 section by section

- Get SPECIFIC answers (no vague responses)

- Clarify cannibalization accounting

- Define authority matrix

- Establish P&L thresholds

- Decide automation levels

### After Wednesday Meeting:

- Sammy analyzes completed questionnaire

- Creates Project Plan v3 (final)

- Create detailed module specifications

- Stakeholder approval on v3

- Begin Phase 1 execution

## FINAL NOTES

This is a well-planned project. The meeting revealed complexity, not problems.

Key Insights: - Grest’s business runs on expert judgment - ERP should ASSIST judgment, not replace it - P&L calculation is the core decision engine - Cannibalization is real and needs proper accounting - Exception states must be explicit - Authority boundaries must be clear

Document Version: 2.0
Previous Version: 1.0 (February 17, 2025)
Next Review: After Wednesday Meeting (February 26, 2025)
Maintained by: Samret Singh

ARCHITECTURAL HARDENING ADDENDUM – VERSION 3.0

1. DEVICE COST LEDGER (FOUNDATIONAL ADDITION)

Each device (GSN) will maintain an immutable Device Cost Ledger capturing:

• Purchase Cost

• Repair Parts Cost (auto accumulated)

• Labor Cost

• Cannibalization Recovery Value

• Final Sale Value

• Net Margin (frozen at closure)

This ledger becomes the atomic profitability record per device and powers long-term margin analytics.

2. STATE MACHINE FREEZE POLICY

The device lifecycle is structurally immutable after Phase 0 sign-off.

• State names cannot be changed post go-live without migration planning.

• States cannot be merged or removed without architectural review.

• All transitions logged with timestamp and user ID.

• Lifecycle version tagged as v1.0 at Phase 0 completion.

3. ACCOUNTING FREEZE GATE (PHASE 0 BLOCKER)

Before Phase 2 begins, the following MUST be finalized:

• Inventory valuation method (FIFO / Average / Standard).

• Cannibalized part valuation logic.

• Scrap write-off accounting treatment.

No TRC build proceeds until accounting method is formally documented.

4. POST GO-LIVE GOVERNANCE FRAMEWORK

After go-live, the following governance rules apply:

• New grades require Admin approval.

• Margin thresholds configurable but logged.

• P&L formula modification requires architecture review.

• New states require formal lifecycle version increment.

• Direct production database edits prohibited.

5. PARALLEL RUN CONTROL ENHANCEMENT

During parallel run:

• Google Sheets transitions to READ-ONLY mid-parallel phase.

• Daily reconciliation owner defined and documented.

• Cutover date escalation required if delayed.

Document Updated: February 24, 2026

Version: 3.0 – Architecturally Hardened Edition