GREST ODOO ERP

Comprehensive Implementation Plan

Version 1.0

Prepared by: Samret Singh + Astra

February 17, 2025

# PROJECT OVERVIEW

A complete ERP system on Odoo Community Edition replacing 30+ Google Sheets — tracking every device from procurement through quality check, repair, and multi-channel sales.

## Timeline

Duration: 12 weeks

Start: Week of February 17, 2025

Go-Live: Week of May 12, 2025

# ONE PHONE'S JOURNEY

This explains how a device flows through the system:

## Step 1: Warehouse Arrival

Phone arrives. Team scans IMEI. Odoo creates record. Barcode generated automatically.

Benefit: Digital identity from moment of entry.

## Step 2: TRC Quality Check

Transferred to TRC (one click). Technician scans, grades device. System auto-decides: B- or better goes to ready stock. C+ or worse goes to repair.

Benefit: No paper. System knows where every phone is.

## Step 3: Repair Decision

Profitability shown automatically:

Purchase: ₹6,850 + Spare: ₹1,200 + Labour: ₹400 = ₹8,450

After-repair value: ₹9,500

Profit: ₹1,050 ✓

Benefit: No repair without profitability check.

## Step 4: Ready Stock

Live dashboard shows inventory by channel, aging, category. All clickable.

Benefit: Complete visibility. Real time.

## Step 5: Sale

Teams see allocated inventory. Mark sold. Updates instantly. D2C syncs to Shopify.

Benefit: No 'is this available?' calls.

# WHAT GREST GAINS

• Search any IMEI in 3 seconds (not 15 minutes)

• Automatic profitability check before repairs

• Aging visibility to act before value loss

• Complete audit trail (who did what, when)

• Shopify always accurate (no overselling)

# IMPLEMENTATION PHASES

## Phase 1: Foundation (Weeks 1-2)

Goal: Configure Odoo to mirror Grest structure

• Create warehouse (GRG) with 10 locations

• Set up 24 product categories

• Configure 9 device grades (A+ to E)

• Add custom fields (IMEI, grades, pricing)

• Import 30 vendors

• Import 106 device models with pricing

• Create 100 user accounts with permissions

Deliverable: Odoo ready for data

## Phase 2: Data Migration (Weeks 3-4)

Goal: Move all historical data from Google Sheets

• Import 14,000 purchase records

• Import 8,000+ spare parts

• Import 2,336 QC records

• Import 6,547 repair records

Deliverable: Complete history in Odoo

## Phase 3: Custom Modules (Weeks 5-8)

Goal: Build smart business logic

• TRC workflow automation

• Profitability engine (auto-calculate repair P&L)

• ELS routing (grade-based decisions)

• Operations dashboard

Deliverable: Automation live

## Phase 4: Integrations (Weeks 9-10)

Goal: Connect external systems

• Shopify sync (bidirectional)

• Grest Partners platform

Deliverable: All systems connected

## Phase 5: Go-Live (Weeks 11-12)

Goal: Training and cutover

• Train 100 users (by role)

• Run parallel (Sheets + Odoo) for 1 week

• Cutover: Sheets go read-only

• Hypercare support

Deliverable: Google Sheets retired

# SUCCESS METRICS

## Technical

☐ All 30,000+ records migrated

☐ Real-time updates < 1 second

☐ All 100 users can login

☐ Shopify sync working

## Business

☐ IMEI search < 3 seconds

☐ Profitability auto-calculated

☐ Zero inventory discrepancy

☐ Dashboard live numbers accurate

# IMMEDIATE NEXT STEPS

## This Week

Day 1: Approve plan, create warehouse in Odoo

Day 2: Create locations and categories

Day 3: Add custom fields

Day 4: Create operation types and user groups

Day 5: Create test users, report progress

Week 1 Deliverable: Odoo ready for data migration

— End of Document —